## Sheet1
Date | time axis 2017-03-24 to 2017-06-29
Day |  |  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
Deliverable | Task | Subtask
Requirements Analysis |  |  | 2017-03-24: Completed
Design Approach
Preliminary Research | bar: 2017-03-25 to 2017-03-29
Individual Submission
|  | Written Report | 2017-04-04: Submit 4pm
|  | Assessed Interview Prep | 2017-04-07: Submit 12
Group Submission
|  | Written Report | 2017-04-13: Submit 4pm
Design Review
Group Submission
Internal Design Review | bar: 2017-04-25 to 2017-04-28
|  | Design Review Meeting | 2017-04-28: 12 midday
Final Report
Preliminary Research
Size the System | bar: 2017-04-14 to 2017-04-17; 2017-04-19 to 2017-04-20
Research Specific Technologies | bar: 2017-04-14 to 2017-04-17; 2017-04-19 to 2017-04-20
Compare Hybrids | bar: 2017-04-19 to 2017-04-20; 2017-04-28 to 2017-05-01
Simulations W.R.T. RA | bar: 2017-04-18 to 2017-04-20; 2017-04-28 to 2017-05-03
Decision Deadlines
Choose specific technologies
Eliminate one hybrid option
Stop researching and simulating
Individual Submission
|  | Written Report | 2017-05-17: Submit 4pm
|  | Assessed Interview Prep | 2017-05-19: Submit 12
Group Submission
|  | Written Report | 2017-05-26: Submit 4pm
|  | Other Products | 2017-05-26: Submit 4pm
Presentation
Group Submission
|  | Create Presentation Slides | 2017-06-02: Submit 7am
Write Presentation Script | bar: 2017-05-30 to 2017-06-01
|  | Give Presentation | 2017-06-02: 12 midday
|  | Present Other Products | 2017-06-02: 12 midday
Team Wind-down
Group Submission
|  | Grab a beer! | 2017-06-02: 5pm